DRAFT PERFORMANCE IMPROVEMENT OBJECTIVES 2026-2027

CONSULTATION DOCUMENT

| Contents | Page |
| --- | --- |
| Introduction | 3 |
| Consultation Process | 5 |
| Summary Tables of Draft Performance Improvement Objectives 2026-27 PIO 1: We will reduce the average number of days sickness absence lost per employee. PIO 2: We will reduce Council’s environmental impact through the development and implementation of a Climate and Sustainability Action Plan. PIO 3: We will improve our Waste Management Services through the implementation of technological solutions and continued communication. PIO 4: We will improve the Council’s Cemetery Service to ensure a safe, high-quality, customer-focused, and resilient bereavement service. PIO 5: We will improve recruitment processes to ensure vacancies are filled in a timely manner. | 7 |
| We want to hear from you | 12 |
| Consultation Questionnaire | 13 |

Introduction

Armagh City, Banbridge and Craigavon Borough Council has a statutory duty under the Local Government Act (Northern Ireland) 2014, to publish improvement objectives each year which set out the key improvements Council aims to deliver.

Essentially, improvement is about making things better, with continuous improvement focusing on ensuring sustainable, on-going improvements to the way we as a Council work and deliver our services.

As per Department for Communities (DfC) Government Guidance, our draft improvement objectives have been based on:

- a strong evidence base,

- an understanding of our citizens’ needs,

- correspond directly with Council’s priorities, and

- selected on basis of critical self-analysis.

In this document, we are pleased to introduce our draft Performance Improvement Objectives for 2026/2027 and invite you to put forward your views on these objectives.

They are as follows, with further details on each of the objectives is set out later in this document:

PIO 1: 	We will reduce the average number of days sickness absence lost per employee.

PIO 2: 	We will reduce Council’s environmental impact through the development and implementation of a Climate and Sustainability Action Plan.

PIO 3:	We will improve our Waste Management Services through the implementation of technological solutions and continued communication.

PIO 4:	We will improve the Council’s Cemetery Service to ensure a safe, high-quality, customer-focused, and resilient bereavement service.

PIO5:	We will improve recruitment processes to ensure vacancies are filled in a timely manner.

We are committed to ensuring that our performance improvement objectives positively enhance the quality of life for all stakeholders across the Borough. Our goal is to provide assurance to residents, businesses, and all stakeholders that we are dedicated to delivering services that are efficient, cost-effective, and of the highest standard.

The purpose of this document is to invite your feedback on the draft Performance Improvement Objectives for 2026-2027. We value your ongoing input and welcome any comments, suggestions, or ideas for new improvement objectives that could help us further enhance our services.

Consultation Process

In preparing the draft Performance Improvement Objectives for 2026-27, we have drawn on a wide range of evidence, including data, performance reports, committee reports, and other relevant information.

Since Autumn/Winter 2025, we have undertaken internal analysis and engagement within the Council, involving senior management and officers across all Directorates. This process has included:

- Self-analysis by Heads of Department, examining departmental data, business plans, performance and risk management records and reports, and the Mid-Year Self-Assessment Report.

- Peer analysis within Heads of Department/ Senior Leadership Team to consult with and foster cross-departmental insights.

- Independent critical analysis conducted by the Performance Team, ensuring a continuous improvement focus throughout the review process.

These efforts have been instrumental in shaping the identification of our improvement objectives. To build on this work, we are now undertaking a minimum of 8-week public consultation to gather further feedback and insights from stakeholders.

The consultation will -	Open:	5 FEBRUARY 2026 and close: 2 APRIL 2026

You can submit your feedback to us in the following ways:

Online: 	Armagh City, Banbridge and Craigavon Borough Council - Citizen Space

Email:		performance@armaghbanbridgecraigavon.gov.uk

In Writing:	Strategy & Performance Department

Armagh City, Banbridge and Craigavon Borough Council

Armagh Old City Hospital

39 Abbey Street

Armagh

BT61 7DY

Tel:		0300 0300 900

We will use a range of communication methods to promote the consultation exercise including for example: social media, email, and website.

Hard copies are also available upon request via email, phone or in writing using the contact details above.

The documents are also available in alternative formats upon request using the contact details above.

The relevant equality screening and rural needs impact assessment of the draft performance improvement objectives are included as part of the consultation papers and process.

Upon completion of the public consultation exercise, analysis of feedback and any required changes will be reviewed and subject to Council approval, we will publish an annual Performance Improvement Plan containing the agreed Improvement Objectives for 2026 – 2027 on the Council website at www.armaghbanbridgecraigavon.gov.uk

In the next section of our Consultation document, a table provides detail on each of the 5 Draft Performance Improvement Objectives we have identified. In presenting each of these Objectives for consultation we have highlighted:

- How each objective links with ‘Connected’ - our Community Plan,

- How each objective links to the priorities and commitments within our Corporate Plan

- Why we have chosen the objective

- What we will do to achieve the objective – Our Actions

- How we will measure success – Our Performance Indicators

- What success will look like – Our Targets

- How our Citizens and stakeholders will benefit

- Which Aspects of Improvement we are addressing

Draft Performance Improvement Objectives identified for 2026-27

The tables below provide examples of actions, performance measures, and potential benefits in relation to the draft objectives, which are subject to consultation.

| Performance Improvement Objective 1 | Link to Community Plan/ Corporate Plan 2023-2027 | Why have we chosen this Objective? | What we will do (Actions) | How do we measure (Performance Indicators) | We will have succeeded if (Standards/Targets) | How our citizens and stakeholders may benefit |
| --- | --- | --- | --- | --- | --- | --- |
| We will reduce the average number of days sickness absence lost per employee. | Service Delivery: Continuously review to improve our services. Monitor and report our performance. Staff, Leadership and Resources: Value staff and be civic leaders. Strengthen our governance and review efficiency of our resources and assets | This objective has been retained for 2026/27. The management of absenteeism remains a high priority within Council and will therefore remain an improvement objective. Musculoskeletal, work related and non-worked related stress have remained as the top 3 reasons for absence. | Human Resource and Organisational Development Department to provide support to line managers enabling them to effectively manage staff absence. | The average number of days sickness absence lost per employee. | 16 days or lower | This objective will contribute to the overall health and well-being of our Borough, as a large majority of our employees reside in the Borough. If progress is made, then it should also result in better continuity of service delivery. |
|  |  |  | Develop and implement annual Staff Health & Wellbeing Action Plan. | Staff Health & Wellbeing Action Plan delivered | 31 March 2027 |  |
|  |  |  | Internal review and analysis of absence across all departments. | Report and analysis completed using internal Quality Management System | Quarterly Reports |  |
|  |  |  | Deliver initiatives / activities aligned to main reasons for absence. | Wellbeing initiatives delivered across main themes of absence. | 31 March 2027 |  |
|  |  |  | Maintain a minimum of 85% of Mental Health First Aider (MHFA) Champions within Council and provide as required provide refresher training. | The percentage of Mental Health First Aiders available | 85% |  |
|  |  |  | Communicate MHFA Champions to staff | The number of targeted communications on MHFA services issued to staff. | At least 2 |  |
| Performance Improvement Aspects: Strategic Effectiveness, Service Quality, Service Availability, Fairness |  |  |  |  |  |  |

| Performance Improvement Objective 2 | Link to Community Plan/ Corporate Plan 2023-2027 | Why have we chosen this Objective? | What we will do (Actions) | How do we measure (Performance Indicators) | We will have succeeded if (Standards/Targets) | How our citizens and stakeholders may benefit |
| --- | --- | --- | --- | --- | --- | --- |
| We will reduce Council’s environmental impact through the development and implementation of a Climate and Sustainability Action Plan 2025-2030 | Environment and Place: Actively respond to the climate crisis and support others to do likewise Service Delivery: Monitor and communicate our performance Staff, Leadership and Resources: Strengthen our governance and review efficiency of our resources and assets | This objective has been retained and revised for 2026/27. It is acknowledged that this is a long-term objective for Council and that there is still a significant amount of work to be carried out to ensure that Council deliver on the commitment to reduce their environmental impact. | Cross departmental working group operational. | Working Group meetings | Regular meetings and reporting from Working Group throughout 2026/27. | In the long term there will be a reduction in energy costs and a positive impact on the health and well-being of our citizens. |
|  |  |  | Implementation of the Climate and Sustainability Action Plan 2025-2030. | Action Plan implemented (Regulatory Reporting) | 20% of action plan implemented by 31 March 2027(subject to review) |  |
|  |  |  | Project Proposals and Business cases relating to ‘invest to save’ aligned to action plan. | Business cases developed and approved | 100% of Business cases approved. |  |
|  |  |  | Identify areas of improvement in terms of systems & processes relating to energy usage and cost savings. | The percentage reduction in energy consumption. | 5% reduction in energy consumption across portfolio of facilities, (subject to review) |  |
|  |  |  | Updated Communications on Climate through regular review and update of the Internet/intranet | Frequency of review and update | Quarterly |  |
|  |  |  | Deliver and maintain mandatory staff training | The percentage of staff trained (new and existing) | 70% (subject to review) |  |
| Performance Improvement Aspects: Strategic Effectiveness, Service Quality, Service Availability, Fairness, Sustainability, Efficiency, Innovation. |  |  |  |  |  |  |

| Performance Improvement Objective 3 | Link to Community Plan/ Corporate Plan 2023-2027 | Why have we chosen this Objective? | What we will do (Actions) | How do we measure (Performance Indicators) | We will have succeeded if (Standards/Targets) | How our citizens and stakeholders may benefit |
| --- | --- | --- | --- | --- | --- | --- |
| We will improve our Waste Management Services through the implementation of technological solutions and continued communication. | Service Delivery: Continuously review to improve our services Seek and use regular customer engagement and feedback. Staff, Leadership and Resources: Communicate and engage with staff, communities, and others. | This objective has been retained and revised for 2026/27. A review of performance at Mid-Year showed that whilst good progress has been made in relation to the communications element, the in-cab technology has been delayed. | Continued Implementation of in-cab technology, to include training and awareness | In-cab Technology in use. | 100% of waste collection service using in cab technology | Increased customer satisfaction with information about Waste Management Services. Customers will have improved accessible information on Waste Management Services on a range on channels. |
|  |  |  |  | Development of Training and awareness material | Training Records and Materials available |  |
|  |  |  |  | Availability of real time data and analytical reports. | Weekly and as required. |  |
|  |  |  | Update Waste Management section of website, including Frequently Asked Questions (FAQ) | Frequency of updates | Quarterly |  |
|  |  |  | Provide standardisation of relevant, accurate and up to date information on all appropriate communication channels | Regular standardised up to date information on all appropriate communication channels issued throughout 2026/27 | Throughout 2026/27 as required |  |
|  |  |  | Undertake regular Analysis of customer communication methods including Departmental Contact Us/ complaints/ Website hits/ ABC Council App Usage/social media | Frequency of review ABC Council App usage statistics The number of hits on website section | Quarterly Quarterly Review (will determine baseline) |  |
| Performance Improvement Aspects: Strategic Effectiveness, Service Quality, Service Availability, Fairness, Efficiency, Innovation |  |  |  |  |  |  |

| Performance Improvement Objective 4 | Link to Community Plan/ Corporate Plan 2023-2027 | Why have we chosen this Objective? | What we will do (Actions) | How do we measure (Performance Indicators) | We will have succeeded if (Standards/Targets) | How our citizens and stakeholders may benefit |
| --- | --- | --- | --- | --- | --- | --- |
| We will improve the Council’s Cemetery Service to ensure a safe, high-quality, customer-focussed, and resilient bereavement service | Service Delivery: Continuously review to improve our services Seek and use regular customer engagement and feedback. Staff, Leadership and Resources: Communicate and engage with staff, communities, and others. | This is a new objective for 2026/27. The delivery of a Cemetery Service is one of the primary functions of local councils. A service review identified a number of areas that could be improved to ensure a fit for purpose, resilient Cemetery Service for the future. | Review cemetery staffing structure and job descriptions. | Review of Cemetery Staffing Structure and job descriptions completed | .By 31 March 2027. | Provision of a safer, inclusive, and modern cemeteries service. An improved quality of service for all stakeholders (the public, funeral directors, memorial masons, and clergy) including better access to information. |
|  |  |  | Procure new cemetery software to enhance accessibility of the burial booking system. | Software procured and in use | By 31 March 2027 |  |
|  |  |  | Review of current out of hours arrangements | Out of hours arrangements reviewed and outcomes implemented. | By 31 March 2027 |  |
|  |  |  | Review Council website content and update | Website Updated | By 31 March 2027 |  |
|  |  |  | Purchase equipment to increase safety and dignity | Equipment purchased and in use | By 31 March 2027 |  |
|  |  |  | Introduce a programme of memorial safety inspections | Memorial safety inspection programme developed and programme in place | By 31 March 2027 |  |
| Performance Improvement Aspects: Strategic Effectiveness, Service Quality, Service Availability, Fairness, Efficiency, Innovation |  |  |  |  |  |  |

| Performance Improvement Objective 5 | Link to Community Plan/ Corporate Plan 2023-2027 | Why have we chosen this Objective? | What we will do (Actions) | How do we measure (Performance Indicators) | We will have succeeded if (Standards/Targets) | How our citizens and stakeholders may benefit |
| --- | --- | --- | --- | --- | --- | --- |
| We will improve recruitment processes to ensure vacancies are filled in a timely manner. | Service Delivery: Continuously review to improve our services. Staff, Leadership and Resources: Communicate and engage with staff, communities, and others | This objective is new for 2026/27 This performance improvement objective will help ensure consistent service delivery, attract and retain candidates through the recruitment process and support workforce planning | Continue to implement the new Recruitment Procedure and Guidance, effective from July 2025 | Recruitment Procedure and Guidance implemented | Recruitment Procedure and Guidance implemented by 31 March 2027 | This objective will contribute to the overall service delivery to citizens/ rate payers of the Borough, as improvements will be made to expedite recruitment timelines and ensure staff vacancies are fulfilled effectively. If progress is made, then it should also result in better continuity of service delivery. Improved recruitment experience. |
|  |  |  | Undertake an end-to-end process review, from approval of vacancy through to appointment date | End to end process review completed with improvements identified and implemented. | By 31 March 2027. |  |
|  |  |  | Set target timelines for each stage of the recruitment process. | Target timelines and % vacancies filled within target timeframe. | % Vacancies filled within target timeframe (Target to be set upon completion of end-to-end review) |  |
|  |  |  | Continue to deliver improvements via digitalisation. | Delivery of improvements. | By 31 March 2027. |  |
|  |  |  | Expand our use of recruitment pools for high volume roles | Use of recruitment pools for high turnover roles. | Continued use of recruitment pools. |  |
| Performance Improvement Aspects: Strategic Effectiveness, Service Quality, Service Availability, Efficiency, Fairness |  |  |  |  |  |  |

We want to hear from you at any time:

We value your feedback and comments on the draft Performance Improvement Objectives. We also welcome any suggestions on how we might improve our services generally and if you would like to propose any new improvement objectives for future consideration.

To get in touch please use any of the following methods:

Email:		performance@armaghbanbridgecraigavon.gov.uk

Telephone:	0300 0300 900, ask for the Strategy and Performance Department

In Writing:	Strategy and Performance Department

Armagh City, Banbridge and Craigavon Borough Council

Armagh Old City Hospital

39 Abbey Street

Armagh

BT61 7DY

CONSULTATION QUESTIONNAIRE

Armagh City, Banbridge and Craigavon Borough Council is conducting a consultation to seek your views on its draft performance improvement objectives for 2026-2027.

The Local Government Act (NI) requires councils to ensure continuous improvement whilst carrying out their functions and delivering their services. Councils are also required to set improvement objectives and put in place arrangements to achieve these.

The Council is dedicated to ensuring that its performance objectives positively impact the quality of life for stakeholders across the Borough. We strive to build confidence among residents, businesses, and all stakeholders in our commitment to delivering services that are efficient, effective, and of the highest standard.

The purpose of this consultation is to seek your views on the draft improvement objectives for 2026-2027, the associated Equality Policy Screening form and the Rural Needs Impact Assessment.

We welcome your feedback and suggestions on how we can make improvements in any service area.

You can request alternative formats of the questionnaire by contacting the Performance Team using the details below:

By email:	performance@armaghbanbridgecraigavon.gov.uk

By telephone:	0300 0300 900, ask for the Strategy & Performance Department.

In writing to:	The Performance Team

Armagh City, Banbridge and Craigavon Borough Council

Armagh Old City Hospital

39 Abbey Street

Armagh

BT61 7DY

Responses should be returned, no later than 2 APRIL 2026 via Council’s Consultation Hub using the link: Armagh City, Banbridge and Craigavon Borough Council - Citizen Space or by using the contact details listed above. If you require assistance, then please do not hesitate to contact us

PRIVACY NOTICE FOR DRAFT PERFORMANCE IMPROVEMENT OBJECTIVES 2026-27

Purpose and lawful basis for processing

Our purpose for processing your personal data is to obtain your views on draft Performance Improvement Objectives which we set within our annual Performance Improvement Plan for 2026-2027. We want these objectives to have a positive impact on the quality of life for all stakeholders across the Borough.

We are processing the personal information you provide under the UK General Data Protection Regulation (UK GDPR). The lawful basis we are relying on to process your personal data is Article 6 (1) (c) of the UK GDPR, which allows us to process personal data when the processing is necessary for Council to comply with the law (not including contractual obligations).

What do we need?

We only collect and use the minimum amount of personal information required. The information that we will collect about you in this consultation is:

- Name

- Postcode

- Email Address

When you complete our online consultation, we collect the IP address that you accessed from but do not use this to identify individuals.

We will also process any other personal data you choose to provide in your response to the consultation such as the EQIA (Equality) Policy Screening Form and your response to the Rural Needs Impact Assessment.

You also have the option of providing monitoring information, recorded separately from your response to the consultation, and which remains anonymous.

What do we do with it?

We will process personal information provided to obtain your feedback on draft Performance Improvement Objectives for 2026-27.

We may publish a summary of the consultation responses, but this will not contain any personal data.

How long do we keep it?

This consultation is available from 5 February 2026 and closes on 2 April 2026. The responses will be securely stored electronically on servers, held for six years from the consultation closing date, and then deleted / destroyed in line with Council’s Retention and Disposal Schedule. Your personal data will be destroyed following the completion of analysis.

Do we use any data processors?

Council has a contract with Delib Citizen Space to provide the Consultation Hub service as a method to gather the consultation responses. This service provides the online consultation platform for Council to design and publish online public engagement activities including consultations. This is also the service used by Council when it commissions third parties to carry out engagement activities, unless otherwise stated.

Council is the data controller, Delib is the data processor and Rackspace Limited, which hosts the consultation platform, is a sub-processor. You can find details of the Consultation Hub’s privacy policy via armaghbanbridgecraigavon.citizenspace.com/privacy policy.

You can find privacy statements relating to Delib’s service to its customers and their Data Protection Officer’s contact details via www.delib.net/privacy.

Where is the information stored? Do we transfer data overseas?

All data collected through this consultation is stored in the UK in secure data centres operated and managed by Delib’s chosen Infrastructure as a Service provider. You can find details of the Consultation Hub’s privacy policy at the following link:

armaghbanbridgecraigavon.citizenspace.com/privacy policy.

You can find privacy statements relating to Delib’s service to its customers and their Data Protection Officer’s contact details via www.delib.net/privacy.

What are your rights?

If you have any questions regarding this survey, or you wish to withdraw from the consultation, please contact the Strategy & Performance Department:

In writing:	Strategy & Performance Department

Armagh City, Banbridge and Craigavon Borough Council

Armagh Old City Hospital

39 Abbey Street

Armagh

BT61 7DY

By email: 	performance@armaghbanbridgecraigavon.gov.uk

By phone: 	0300 0300 900 and ask for the Strategy and Performance Department.

For more information on your rights, please refer to the Information Commissioner’s Office website please see 'Your data protection rights'.

If you are unhappy with the way in which we have processed your personal data, you have the right to complain to the ICO as the UK supervisory authority.

Please tick this box that you agree before completing the questionnaire.

Questionnaire

Introduction

| Your details: |  |
| --- | --- |
| Name |  |
| Postcode |  |
| Contact Email |  |

| Are you responding as an individual or an organisation? (Please specify) |  |
| --- | --- |
| Individual |  |
| Organisation |  |

If you are responding for an organisation, please specify the name.

| Question 1: What is your main interest in responding to this consultation? Please tick all that apply: |  |
| --- | --- |
| Resident |  |
| Elected Member |  |
| Local Business |  |
| Local Community Organisation |  |
| Local Voluntary Organisation |  |
| Statutory Organisation |  |
| Current Council Employee |  |
| Visitor to the Borough |  |
| Work in the Borough |  |
| Other |  |

If other, please provide further detail below:

| Question 2: Proposed Performance Improvement Objectives Do you agree that the proposed Performance Improvement Objectives are appropriate for our Borough? As well as the proposed objective, you may wish to reflect on the key actions, measurements and outcomes as described in the consultation document. Please indicate whether you agree or disagree with the proposed Performance Improvement Objective in the tick box provided. You may also wish to consider the additional prompts and provide comments in the boxes below. |  |  |  |  |
| --- | --- | --- | --- | --- |
| 1. We will reduce the average number of days sickness absence lost per employee. Council wish to contribute to the overall health & wellbeing of our Borough, this includes our own workforce. | Agree |  | Disagree |  |
| Comments: |  |  |  |  |

| 2. We will reduce Council’s environmental impact through the development and implementation of a Climate and Sustainability Action Plan. You may wish to let us know of initiatives/ideas Council could consider in relation to this objective. | Agree | Disagree |
| --- | --- | --- |
| Comments: |  |  |
| 3. We will improve our Waste Management Services through the implementation of technological solutions and continued communication. You may wish to let us know of ideas/initiatives Council could consider in improving our communications in relation to waste management services. | Agree | Disagree |
| Comments: |  |  |
| 4. We will Improve the Council’s Cemetery Service to ensure a safe, high-quality, customer-focussed, and resilient bereavement service. Council wants to ensure the provision of a safer, more modern and resilient cemetery service. | Agree | Disagree |
| Comments: |  |  |
| 5. We will improve recruitment processes to ensure vacancies are filled in a timely manner. Council wants to ensure that recruitment processes are effective, and to ensure every candidate knows what is expected and Council can plan accordingly. Timely recruitment will have a positive impact on service delivery. | Agree | Disagree |
| Comments: |  |  |

Question 3: Suggestions For Improvement Council is committed to their General Duty to Continuously Improve. If there are other specific Council Services where you would like to see improvements made, please provide detail in the space below.

Comments:

| Question 4: Equality Do you feel the draft Armagh City, Banbridge and Craigavon Borough Performance Improvement Objectives would have a positive or negative effect on the following (tick the box) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Strongly Positive |  | Mainly positive | No effect | Mainly negative | Strongly negative |
| Persons with/without dependants |  |  |  |  |  |  |
| Persons with/without a disability |  |  |  |  |  |  |
| Men and Women |  |  |  |  |  |  |
| Sexual Orientation |  |  |  |  |  |  |
| Marital Status |  |  |  |  |  |  |
| Racial Groups |  |  |  |  |  |  |
| Different ages |  |  |  |  |  |  |
| Political Opinion |  |  |  |  |  |  |
| Religious Belief |  |  |  |  |  |  |
| Comments: |  |  |  |  |  |  |

Question 5: EQIA Policy Screening form If you have any further comments on the EQIA Policy Screening form, please comment below.

Comments:

Question 6: Rural Needs Impact Assessment Do you agree that the draft performance improvement objectives will have a positive impact on the Rural needs within our Borough? YES; NO. If you have any further comments on draft Rural Needs Impact Assessment, please comment below.

Comments:

Thank you for taking part in this consultation, your views are appreciated.

All responses received will be analysed and complied into an anonymous consultation report.

Feedback on the consultation responses will be provided on the Council website via the ‘We asked, You Said, We Did’ section of our consultation hub.